## Sheet1
Audit Log Planning (Defenders)
Epic | Epic Name | Ticket ID | User Stories | Assigned To | Status | Start Date | End Date | Duration (In day)
1 | Rest API Creation in Spring Boot Application | AL-1 | Read All Controller | Roshani &Aishwarya | Done | 2022-09-12 | 2022-09-14 | 3
|  | AL-2 | Read All Service | Pratik | Done | 2022-09-12 | 2022-09-14 | 3
|  | AL-3 | Search Controller | Amey | Done | 2022-09-12 | 2022-09-14 | 3
|  | AL-4 | Search Service | Surbhit | Done | 2022-09-12 | 2022-09-14 | 3
2 | UI and It's integration with Spring boot Application | AL-5 | Home Webpage | Aishwarya & Amey | Done | 2022-09-15 | 2022-09-16 | 2
|  | AL-6 | View LogsWebpage | Roshani | Done | 2022-09-15 | 2022-09-16 | 2
|  | AL-7 | Search Logs Webpage | Pratik | Done | 2022-09-15 | 2022-09-16 | 2
|  | AL-8 | Added Rest Template | Surbhit | Done | 2022-09-15 | 2022-09-16 | 2
3 | UI Improvement | AL-9 | Improvement in Homepage | Aishwarya | Done | 2022-09-19 | 2022-09-20 | 2
|  | AL-10 | Added Logo of Audit log | Roshani | Done | 2022-09-19 | 2022-09-20 | 2
|  | AL-11 | Changed Alert Messages | Surbhit | Done | 2022-09-19 | 2022-09-20 | 2
|  | AL-12 | Improvement in View Logs webpage | Pratik | Done | 2022-09-19 | 2022-09-20 | 2
|  | AL-13 | Improvement in Search Logs webpage | Amey | Done | 2022-09-19 | 2022-09-20 | 2
4 | Documentation & Testcases | AL-14 | Postman JSON Collection | Aishwarya | Done | 2022-09-21 | 2022-09-22 | 2
|  | AL-15 | Test Cases(+ve) | Surbhit | Done | 2022-09-21 | 2022-09-22 | 2
|  | AL-16 | Test Cases(-ve) | Roshani | Done | 2022-09-21 | 2022-09-22 | 2
|  | AL-17 | Audit Log Report | Amey & Pratik |  | 2022-09-21 | 2022-09-22 | 2